## Test Plan
Test Plan
Test Plan : | https://www.demoblaze.com/
Introduction: | testing strategy will use the manua test and set test cases & Bug report and script automation
Objectives: | Ensure that all functionalities meet specified requirements the E-commerce
Test Scope: | This test covers functionalities, but not system security
Date: 01.04.2025 | Updated on: 12.04.2025
4
Test Items | Test Environment & Tools | Test Types | Test Strategy and Approach | Entry Criteria | Exit Criteria | Deliverables | Start Date | End Date | Assignee | KPIs | Notes
Started | Server | functional | unit testing | all functional requirements must be finalized and approved | at least 95% of the planned test cases must be executed | document listing all test cases | 01.04.2025 | 15.04.2025 | AMIR HAMED | test case execution rate: executed test cases/total test cases x 100
In Progress | Client machines | functional | integration testion | test cases must be written, reviewed and approved | a mimimum of 90% of executed test cases must pass | report summarizing outcomes of test case executions | 01.4.2025 | 10.15.24 | Hend Magdy | pass rate: passed test cases/executed test cases x 100
In Progress | Server | functional | Automation approach using Selenium WebDriver and Java | Initial framework setup completed JIRA, Postman, and Selenium tools installed and configured | thresholds met Final report and documentation delivered | Automated test suite | 2.4.2025 | 15.4.2025 | Rawan Eldeeb | automation coverage
Started | Browsers: Chrome, Firefox Tools: Selenium, Postman, JMeter, JIRA, TestNG, Jenkins OS: Windows/macOS , Java | Automation | Postman used for API testing, and JMeter for performance testing. JIRA will track bugs and test cases |  |  |  |  | 15.4.2025 | Rawan Eldeeb | load performance metrics
Test Plan Team
Name | Role | Responsibilities
AMIR HAMED | QA | test functionality | Server
Hend Magdy | QA | test functionality | Client machines
Rawan Eldeeb | QA | Automation